## Sheet1
|  |  |  | ISV | OEM | M-ISV
| ISV/OEM/Mobile ISV Initiative |  |  | The Players | [27 empty] | Completed
RASCI Chart |  | Phase | Priority | Joe Smith | John Doe | Sally Smart | John Hancock | [23 empty] | TASK COMPLETED | Date (w/o) | Notes
1 | Business Plan Of Record | Marketing | [5 empty] | S |  |  |  |  | C |  |  |  |  | R |  |  |  | S | [8 empty] | X | 08/05/05 | Approved
2 | Define bundle (hardware, software) config. | Design |  | C |  | C |  | S | C |  |  |  | S | S |  |  |  | S |  |  |  | R | [6 empty] | S |  | X | 08/06/05 | Compaq DL360, DL 380 & Tru64 UNIX
3 | Define bundle consulting services-Nokia Demo | Design |  | C |  | C |  | S | C |  |  |  | S | S |  |  | S | S |  | S | S | R | [5 empty] | S | S | S |  | 03/19/01
4 | Define bundle option advanced consult. serv. | Design |  | C | S |  |  | S | C |  |  |  | S | C |  |  | S | S | S | S | C | R | [5 empty] | R | C | S |  | 03/19/01
5 | Define bundle customer support serv.(lvls1-3) | Design |  | C |  |  |  | S | C |  |  |  | S | S |  |  | C | S |  |  | S | R | [6 empty] | S | C |  | 03/19/01
6 | ROI ofdesign upgrade | Design | [5 empty] | C |  | R |  |  | C | S |  |  |  | S |  |  |  | C |  | S |  |  |  |  | S |  |  | 03/26/01 | Within BEA M-Commerce & Mobile Solutions
7 | Define Reselling (& Services) Agreements | Engagement |  | C |  |  |  | S | C |  |  | C | R | S |  |  |  | S |  |  |  | S |  | C |  |  |  | C | S |  |  | 03/26/01
8 | Price bundle configuration | Marketing |  | C |  |  |  | S | C |  |  | C | S | S |  |  | C | S |  |  |  | R |  | C |  |  | C |  | S | C |  | 03/26/01
9 | Price bundle consulting services | Marketing |  | C |  |  |  | S | C |  |  | C | S |  |  |  | S | S |  | S |  | R |  |  |  |  | C | A |  | S |  | 03/26/01
10 | Price bundle option advanced consult. serv. | Marketing |  | C | S |  |  | S | C |  |  | C | S |  |  |  | S | S | S | S |  | R |  |  |  |  | C | A |  |  |  | 03/26/01
11 | Produce positioning matrix | Marketing | [5 empty] | S | S |  | S |  | S |  |  |  |  | S |  |  |  | R |  |  |  |  | S |  |  |  |  | 03/26/01
12 | Position offering relative to Competition | Marketing |  | S |  |  |  | S | S |  | S |  | S | C |  |  |  | S |  |  |  | R |  | S |  |  | S |  | C |  |  | 03/26/01
13 | Forecast volumes and revenue | Engagement |  | A |  |  |  | A | A |  | A | A | S | S |  |  | C | R |  |  |  | A |  | S |  | C | C | C | S | S |  | 04/02/01 | As of 7/15/05
14 | Execute Reselling (& Services) Agreements | Engagement |  | S |  |  |  | A | A |  | A |  | R | S |  |  | C | A |  |  |  | A |  | S |  |  |  | C | S |  |  | 04/02/01
15 | Define OEM Direct assy. process & reqs. | Manufacturing |  | S |  | S |  | S |  |  | S |  | S | S |  |  |  | R |  |  |  | S |  | C |  |  |  |  | S |  |  | 04/02/01
16 | OEM Direct Assembly trial | Manufacturing |  | S |  | R |  | S |  |  | S |  | S | S |  |  |  | S |  |  |  | S |  | C |  |  |  |  | S |  |  | 04/02/01
17 | Prepare OEM Direct distribution plan | Manufacturing |  | S |  | S |  | S |  |  | S |  | S | S |  |  |  | R |  |  |  | S |  | C |  |  |  |  | S |  |  | 04/02/01 | Determined by GTM strategy & may vary by solution/vertical
18 | Test assembly configurations | Manufacturing |  | S |  | R |  | S |  |  | S |  | S | C |  |  |  | S |  |  |  | S |  | S |  |  |  |  | C |  |  | 04/02/01
19 | Mobile ISV/OEM/ISV Planning Review | Marketing |  | S |  |  |  | R | S |  | S | S | S | S |  |  |  | S |  |  |  | R |  | S |  | S | S |  | S |  |  | 04/02/01
20 | Define SI Mktg messages | Marketing |  | S |  |  |  | S | S |  | S | C | S |  | R |  |  | S |  |  |  | S |  | S |  |  | S |  |  | C |  | 04/09/01
21 | Define Financial Services Mktg messages | Marketing |  | S |  |  |  | S | S |  | S | C | S |  | S |  |  | S |  |  |  | S | R | S |  |  | S |  |  | S |  | 04/09/01
22 | Develop SI Focussed Mktg Demo | Marketing |  | C |  | C |  | S | S |  | S | C | S | C | S |  |  | S |  |  |  | R |  | S |  |  | S |  | C | C |  | 04/16/01
23 | Develop Financial Services Mktg Demo | Marketing |  | C |  | S |  | S | S |  | S | C | S | S | S |  |  | S |  |  |  | S | R | S |  |  | S |  | S | S |  | 04/16/01
24 | OEM internal awareness Event | Marketing |  | S |  | S |  | S | S |  | S | C | S | S | C |  |  | R |  |  |  | S | C | S |  | C | S |  | S |  |  | 09/05-10/05
25 | Draft Sales Tool - "Science of Selling" | Marketing |  | S |  | C |  | S | S |  | S | C | S | C |  |  |  | R |  |  |  | S |  | C |  |  | S |  | C |  |  | 05/21/01
26 | Create printed and PDF brochure | Marketing |  | S |  | C |  | S | S |  | S | C | S |  |  |  |  | S |  |  |  | R |  | S |  |  | S |  |  |  |  | 05/21/01
27 | Update all three partner websites | Marketing |  | S |  | S |  | S | C |  | S | C | S | C |  |  |  | S |  |  |  | R |  | C |  |  | R |  | C |  |  | 05/21/01
28 | Prepare ISV PR (w/ Partner Exec.) | Marketing |  | S |  |  |  | S | C |  | S | C | S |  |  |  |  | S |  |  |  | R |  | S |  |  | S |  |  |  |  | 05/21/01
29 | Secure PR approval | Marketing | [5 empty] | S |  |  |  |  | S |  |  |  |  | S |  |  |  | R |  | S |  |  | S |  |  |  |  | 05/21/01
30 | Secure Partner executives PR quotes | Marketing | [5 empty] | S |  |  |  |  | S |  |  |  |  | S |  |  |  | R |  | C |  |  | S |  |  |  |  | 06/04/01
31 | Gather Feedback from OEM Sales Force | Marketing | [5 empty] | S | S |  |  |  | S |  |  |  |  | R |  |  |  | S | [9 empty] | 06/04/01
32 | Prep OEM NA region sales drivers | Marketing |  | S |  |  |  | S | S |  | S | S | S |  |  |  |  | S |  |  |  | S |  |  | R | S | [5 empty] | 06/04/01
33 | Engage NA OEMPS Sales | Marketing |  | S |  |  |  | S | S |  | S | S | S |  |  |  |  | S |  |  |  | S |  |  | R | S | [5 empty] | 06/04/01
34 | NA Call Center scripts and training | Marketing |  | S |  |  |  | S | S |  | S | S | S |  |  |  |  | S |  |  |  | S |  |  | R | S | [5 empty] | 06/11/01
35 | Prepare NA internal/partner virtual training | Engagement |  | S |  |  |  | S | S |  | S | S | S |  |  |  |  | R |  |  |  | S |  |  | S | S | [5 empty] | 06/11/01
36 | Prepare NA virtual customer awareness | Engagement |  | S |  |  |  | S | S |  | S | S | S |  |  |  |  | R |  |  |  | S |  |  | S | S | [5 empty] | 06/11/01 | May "utilize/dovetail" BEA/Compaq/Nokia Field/Partner events
37 | Schedule NA Partner/Sales force roadshow | Engagement |  | S |  |  |  | S | S |  | S | S | S |  |  |  |  | R |  |  |  | S |  |  | S | S | [5 empty] | 06/11/01 | May "utilize/dovetail" BEA/Compaq/Nokia Field/Partner events
38 | Distribute demo's to Customer Centers & Labs | Engagement |  | S |  | S |  | S | S |  | S | S | S |  |  |  |  | R |  |  |  | S |  | S | S |  | S |  | S |  |  | 06/25/01
39 | Launch at NA Trade Shows: | Marketing |  | S |  | S |  | S | R |  | S |  | S |  | S |  |  | S |  |  |  | R | S | S |  | S | S |  | C |  |  | 10 - 04/06 | Nokia users group meeting, 10/01 in Atlanta, GA
48 | Track opportunities | Engagement |  |  |  |  | S | R | C |  | S |  | S |  |  | S |  | S |  |  |  | S |  |  | S |  | S |  |  |  |  | Monthly | APAC & ROW Rollouts are also dependent on NTT's IMODE standard
49 | Schedule monthly concalls | Engagement | [5 empty] | S | S |  | S |  | S |  |  |  |  | S |  |  |  | R | [9 empty] | Monthly
RASCI Codes
R: Responsible
A: Approve
S: Support
C: Consult
I: Inform